NATIONAL AIDS & STIS CONTROL PROGRAMME

REQUEST FOR PROPOSALS

FOR

Individual Consulting Services

Time-Based Payments

ENGAGEMENT OF CONSULTANT TO LEAD THE GC7 PMTCT ANNUAL PROGRAM ASSESSMENT

January 2026

RFP Ref No:     NASCP/GF/HIV/2026/001

27th January,2026

Letter of Invitation

Dear Sir/Ma:

The Prevention of Mother-to-Child Transmission (PMTCT) programme remains a central pillar of Nigeria’s HIV response, contributing significantly to reductions in vertical transmission of HIV, syphilis, and hepatitis B virus (HBV). Nigeria continues to bear a substantial burden of pediatric HIV infections, making the scale-up and optimization of PMTCT services a national priority.

Under the Global Fund Grant Cycle 7 (GC7), Nigeria has expanded PMTCT services to additional antenatal care (ANC) sites, strengthened HIV testing and linkage for pregnant women (including community-based approaches), improved ART initiation and retention, and enhanced Early Infant Diagnosis (EID). Despite these gains, persistent challenges remain in service quality, implementation efficiency, coordination at state and LGA levels, and integration with other public health programmes such as TB, malaria, and MNCH.

In line with accountability, learning, and continuous improvement principles, NASCP plans to conduct an annual PMTCT program assessment using a systems-strengthening lens to identify strengths, gaps, and opportunities for scale-up and sustainability. To support this process, NASCP seeks to engage a qualified consultant to lead the assessment

2. More details on the requested services are provided in the Terms of Reference in section A below

3. The National AIDS/STIs Control Programme will make available the necessary information concerning this assignment. You may obtain additional information at the following address: National Coordinator, The National AIDS/STIs Control Programme Plot 75, Edo House, Ralph Shodeinde Street, Central Business District, Abuja.

4. Candidates are required to submit the following:

i. Evidence of previous work experience relating to the job role with relevant supporting documents (Supporting documents, award letters, or contracts for similar jobs)

ii. Current Curriculum Vitae and Cover Letter (Proof of certifications mentioned in the CV submitted)

iii. Strong knowledge of Global Fund programmes and Nigeria’s HIV response.

v. Technical Proposal (methodology and work plan)

Please note that selection will be on the basis of comparison of individual qualifications (Curriculum Vitae, Experience and supporting documents provided) and technical proposal

5. The following forms are attached:

(a) Terms of Reference;

(b) Model of Curriculum Vitae.

(c) Proposal.

(d)Observation and suggestion of the consultant on the terms of reference

(e)List of Annex.

i. Annex A (Cost estimate and services

ii. Annex B (Evaluation Criteria)

Yours sincerely,

Pharm. Patiko Mohammed Ibrahim

Deputy Director (PSM)

For National Coordinator

TERMS OF REFERENCE (TOR)

Engagement of a Consultant to Lead the GC7 PMTCT Annual Program Assessment

Background

The Prevention of Mother-to-Child Transmission (PMTCT) programme remains a central pillar of Nigeria’s HIV response, contributing significantly to reductions in vertical transmission of HIV, syphilis, and hepatitis B virus (HBV). Nigeria continues to bear a substantial burden of pediatric HIV infections, making the scale-up and optimization of PMTCT services a national priority.

Under the Global Fund Grant Cycle 7 (GC7), Nigeria has expanded PMTCT services to additional antenatal care (ANC) sites, strengthened HIV testing and linkage for pregnant women (including community-based approaches), improved ART initiation and retention, and enhanced Early Infant Diagnosis (EID). Despite these gains, persistent challenges remain in service quality, implementation efficiency, coordination at state and LGA levels, and integration with other public health programmes such as TB, malaria, and MNCH.

In line with accountability, learning, and continuous improvement principles, NASCP plans to conduct an annual PMTCT program assessment using a systems-strengthening lens to identify strengths, gaps, and opportunities for scale-up and sustainability. To support this process, NASCP seeks to engage a qualified consultant to lead the assessment.

Duration: Three Months

Start Month: February

Location: Abuja

Purpose of the Consultancy

The purpose of this consultancy is to provide technical leadership for the assessment of the performance, quality, efficiency, and integration of the PMTCT Scale-Up Programme under the GC7 grant, and to generate actionable, evidence-based recommendations to accelerate Nigeria’s progress toward elimination of mother-to-child transmission (eMTCT) of HIV, syphilis, and HBV.

Objectives of the Consultancy

The specific objectives of the consultancy are to:

- Document the structures, processes, and implementation modalities of the PMTCT programme under GC7.

- Assess the quality of service delivery across the PMTCT cascade, including ANC, HIV testing, ART initiation, retention, EID, and final outcomes for HIV-exposed infants.

- Evaluate the efficiency of the GC7 PMTCT implementation model and identify operational bottlenecks.

- Assess the level of integration of PMTCT services with TB, malaria, and MNCH programmes.

- Examine state- and LGA-level coordination, governance, and supervisory mechanisms supporting PMTCT implementation.

- Provide practical, evidence-informed recommendations for programme strengthening and sustainability.

Scope of Work

The consultant will undertake the following tasks:

- Programme Implementation Review

- Review GC7 PMTCT programme structures, implementation, funding flows, and roles of implementers (PRs, SRs, States, LGAs, IPs).

- Assess execution mechanisms including supply chain management, human resources, capacity building, data systems, and supervision.

- Quality of Service Delivery

- Evaluate quality of ANC/PMTCT service delivery using agreed indicators, including:

  - ANC coverage

  - HIV testing uptake

  - ART initiation and retention

  - EID at 6 weeks and turnaround times

  - Final outcomes for HIV-exposed infants

  - Syphilis and HBV screening coverage

- Assess client experience, confidentiality, and adherence support mechanisms.

- Efficiency of GC7 Implementation Model

- Analyze financial and human resource efficiency of PMTCT scale-up across conventional and unconventional service delivery sites.

- Identify operational bottlenecks such as funding delays, role duplication, and reporting inefficiencies.

- Explore opportunities to expand stakeholder participation, including civil society, private sector, and faith-based organizations.

- Integration with Other Health Programmes

- Assess integration with TB/HIV collaborative activities.

- Review linkages with malaria and MNCH programmes.

- Identify opportunities for service integration, data harmonization, and joint supervision.

- State and LGA Coordination

- Review coordination and governance structures at state and LGA levels.

- Assess functionality of HIV Technical Working Groups.

- Identify gaps and opportunities for improved alignment across levels.

Methodology

The consultant will support a mixed-methods cross-sectional assessment conducted in 12 states (two per geopolitical zone). The methodology will include:

- Facility record reviews

- Structured interviews with healthcare workers and programme managers

- Focus Group Discussions (FGDs) with pregnant women and mothers

- Direct facility observations

Per state, the assessment will cover:

- Two conventional health facilities (tertiary/secondary/PHC)

- Two unconventional service delivery points (one outreach site and one TBA)

Data collection will be conducted using electronic tools, with built-in quality assurance mechanisms.

Deliverables

The consultant is expected to produce:

- Inception report including refined methodology and tools

- Finalized assessment tools

- Field supervision and quality assurance reports

- Cleaned and analyzed dataset

- Draft assessment report

- Final assessment report incorporating stakeholder feedback

- Presentation of findings to NASCP and key stakeholders

Timeline and Level of Effort

The consultancy will span three (3) months (January – March 2026):

- Month 1: Desk review, tool development, stakeholder engagement

- Month 2: Field data collection and supervision

- Month 3: Data analysis, validation workshops, and reporting

Required Qualifications and Experience

- Advanced degree in Public Health, Medicine, Epidemiology, Health Systems, or related field

- Minimum of 10 years’ experience in HIV/PMTCT programme evaluation or health systems assessments

- Strong knowledge of Global Fund programmes and Nigeria’s HIV response

- Proven experience in mixed-methods research and health programme assessments

- Excellent analytical, writing, and stakeholder engagement skills

10. Ethical Considerations

All assessment activities must adhere to national ethical standards, ensure confidentiality, and protect participant rights. No identifiable personal data shall be included in reports.

Contracting Arrangements

The consultant shall be contracted by NASCP under the GC 7 grant. During the period of assignment s/he will be answerable to NASCP PMU lead as regards the deliverables. S/he will be expected to work with members of staff of NASCP, and other stakeholders. Payment will be made upon NASCPs certification of successful delivery of the deliverables as stipulated.

Milestones-based Payment Plan

| S/No | Description of Deliverable | Means of verification | Timeline (days) | Payment Milestone |
| --- | --- | --- | --- | --- |
| 1 | Desk review, tool development, stakeholder engagement | Submission of the Data Collection tools, implementation road map and activity gannt chart (soft and hard copies) | 22 | 1st |
| 2 | Field data collection and supervision | PMTCT Evaluation data | 22 | 2nd |
| 3 | Data analysis, validation workshops, and reporting | Report of the PMTCT Evaluation | 22 | 3rd |

# 7.0.   Remuneration

S/he will be paid competitive fees for the agreed duration based on qualification and experience and in line with the approved rate for this assignment.

8.0 GUIDELINE FOR SUBMISSION AND OPENING OF DOCUMENTS

A comprehensive Proposal in English shall be prepared and submitted in two (2) hard copies: one original and one duplicate. Each copy (original and duplicate) must be placed in a separate envelope. Both envelopes should then be enclosed within a single outer envelope, securely sealed.

The outer envelope must be clearly labeled in the top-right corner with:
“Engagement of a Consultant to Lead the GC7 PMTCT Annual Program Assessment”

Additionally, the Consultant’s Name, Address, Email, and Phone Number should be prominently written on the back of the outer envelope. The submission should be addressed with acknowledgment to the NASCP office at the address provided below.

9.0.  Address for Submission and Information

Attention:

Deputy Director (PSM)

National AIDS/STIs Control Programme

Edo House,

75 Ralph Shoidende Street,

Central Business District,

Garki, Abuja.

The deadline for the submission of proposal should not be later than Thursday 5th February,2026 by 12 noon.

10.        Global Fund Code of Conduct

The vendor shall get acquainted with the global fund code of conduct for suppliers using this link below: https://www.theglobalfund.org/media/3275/corporate_codeofconductforsuppliers_policy_en.pdf

Accepting this Letter of Award shall serve as an acknowledgement and agreement to abide by the Global Fund Code of Conduct for Suppliers.

| 11. Fraud and Corruption - Whistle blowing and channel of reporting grievances and infractions. | The personnel of the Purchaser and the Suppliers shall adhere to the highest ethical standards, both during the selection process and throughout the execution of the contract. In pursuance of this principle, they shall abstain at all times from corruption or fraudulent practices. Corruption and fraudulent practices are defined as follows: - (i) “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence the action of an official in the selection process or in contract execution; - (ii) “fraudulent practice” means a misrepresentation or omission of facts in order to influence a selection process or the execution of a contract; - “collusive practices” means a scheme or arrangement between two or more suppliers with or without the knowledge of the Purchaser, designed to establish prices at artificial, noncompetitive levels; - “coercive practice” means harming or threatening to harm, directly or indirectly, persons or their property to influence the procurement proceedings, or affect the execution of a Contract. - The Purchaser shall reject a Proposal for award if it determines that the Supplier recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question. - “ « whistle blowing Policy” Suppliers are encouraged to send information on any infraction or grievances to the dedicated email account: nascp@health.gov.ng or +2348161682287 Sexual Exploitation and Abuse and Sexual Harassment 1a. Sexual exploitation and abuse The Donor and NASCP have a zero tolerance for inaction approach to tackling sexual exploitation and abuse (“SEA”). This means NASCP and its implementing partners will take all reasonable steps to prevent SEA by both its employees and any implementing partner and respond appropriately when reports of SEA arise, in accordance with their regulations, rules, policies and procedures. Unless inconsistent with a specific regulation, rule, policy or procedure governing NASCP, NASCP will apply the IASC Six Core Principles Relating to Sexual Exploitation and Abuse (Attachment A) and the following principles and practices when implementing the activities under this arrangement and provide evidence to demonstrate this where required: - Adherence to the IASC-Minimum Operation Standards on “Protection from sexual exploitation and abuse by own personnel” and/or [the] SEA elements of the Core Humanitarian Standard on Quality and Accountability, - A victim/survivor-centred approach to SEA issues; - Strong leadership and signaling on tackling SEA; - Make all reasonable efforts to address gender inequality and other power imbalances; - Reporting to enhance accountability and transparency; - Ensure that SEA standards from this arrangement are reflected in funding templates with implementing partners, and adherence to the NASCP Protocol on Allegations of Sexual Exploitation and Abuse Involving Implementing Partners]. b. Sexual harassment The Donor and NASCP have a zero tolerance for inaction approach to tackling sexual harassment (“SH”). This means NASCP will take all reasonable steps to prevent SH and respond appropriately when reports of SH arise, in accordance with its regulations, rules, policies and procedures. Unless inconsistent with a specific regulation, rule, policy or procedure governing NASCP, NASCP will apply the following principles and practices when implementing the activities under this arrangement: - A victim/survivor-centered approach to SH issues; - Strong leadership and signaling on tackling SH; - Make all reasonable efforts to address gender inequality and other power imbalances; - Reporting to enhance accountability and transparency; 2. NASCP will adhere to the following requirements: a. Allegations of SEA (i) NASCP will promptly report all allegations of SEA credible enough to warrant an investigation through the reporting mechanism. (ii) When NASCP reports an allegation of SEA to, or becomes aware of an allegation reported through, the Report that is (i) directly related to the activities funded by this arrangement or, (ii) would have a significant impact on the partnership between NASCP and the Donor, NASCP will promptly notify Dr. Adebobola Bashorun of the report made and the relevant arrangement number, if applicable and provide information containing the level of detail that NASCP is aware of. (iii) Upon request from the Donor, NASCP agrees to provide further available relevant information NASCP is aware of for allegations notified under paragraph 2a (ii) including about subsequent measures taken by NASCP, unless disclosure of such information would be inconsistent with NASCP’ regulations, rules, policies and procedures concerning disclosure of information b. Allegations of SH (i) NASCP will report allegations of sexual harassment and measures taken through existing reporting mechanisms. (ii) Where NASCP has determined that the allegations would have a significant impact on the partnership between NASCP and the Donor, NASCP will promptly notify Dr. Adebobola Bashorun and provide information containing the level of detail of the existing reporting mechanisms. (iii) Upon request from the Donor, NASCP agrees to provide further available relevant information, that NASCP is aware of unless disclosure of such information would be inconsistent with NASCP’ regulations, rules, policies and procedures concerning disclosure of information. 3. It is understood and accepted that NASCP’ arrangement to report on SEA and SH will be performed in accordance with NASCP’ regulations, rules, policies and procedures, including its rules on confidentiality, and is subject to not compromising the safety, security, privacy and due process rights of any concerned persons. 4. When NASCP becomes aware of reasonable suspicions, complaints or reports of SEA or SH by its personnel, NASCP will, as appropriate under its regulations, rules, policies, and procedures, take reasonable, swift and appropriate action to stop harm occurring, investigate and report to relevant authorities (for potential criminal matters), as appropriate and when safe to do so, after considering the wishes of the victim/survivor. 5. The Donor or any of its duly authorized representatives may, in accordance with agreed mutually accepted terms of reference, carry out reviews or evaluations or other assessment measures to verify NASCP’ zero tolerance for SEA and SH. NASCP will fully cooperate within the scope of the terms of reference with any such reasonable requests by the Donor or any of its duly authorized representatives or agents to carry out such measures. 6. Any information or documentation provided in accordance with these provisions will be treated by the Donor with utmost discretion in order to ensure, inter alia, the probity of any investigation, protect sensitive information, ensure the safety and security of persons and respect the due process rights of all involved. The Donor will presume information/documentation to be confidential, deliberative, and investigatory and will ensure that information/documentation provided to the Donor will be available solely to those who strictly require access to such information/documentation. Any disclosure of such information/documentation beyond such personnel will require notification and consultation with NASCP. The Donor will obtain the express written authorization of NASCP before disclosing any such information/documentation in a judicial proceeding or to the public, unless disclosure is otherwise required by law applicable to the Donor and is not subject to NASCP’ privileges and immunities under international and/or national law. 7. Unless the regulations, rules, policies, and procedures applicable to NASCP are amended at an earlier stage, and/or there are other substantive changes to any of the referenced policies, processes or mechanisms, the above provisions are subject to possible PERIODIC review after the date of the Donors’ mutual decision on their text with NASCP. Any changes to the above provisions that may be mutually decided following such a review will take effect at least four years after the date of the Donors’ mutual decision on the present text with NASCP, until which time the above provisions will continue to apply. Attachment A: IASC Six Core Principles Relating to Sexual Exploitation and Abuse 1. Sexual exploitation and abuse by humanitarian workers constitute acts of gross misconduct and are therefore grounds for termination of employment. 2. Sexual activity with children (persons under the age of 18) is prohibited regardless of the age of majority or age of consent locally. Mistaken belief regarding the age of a child is not a defence. 3. Exchange of money, employment, goods, or services for sex, including sexual favours or other forms of humiliating, degrading or exploitative behaviour is prohibited. This includes exchange of assistance that is due to beneficiaries. 4. Any sexual relationship between those providing humanitarian assistance and protection and a person benefitting from such humanitarian assistance and protection that involves improper use of rank or position is prohibited. Such relationships undermine the credibility and integrity of humanitarian aid work. 5. Where a humanitarian worker develops concerns or suspicions regarding sexual abuse or exploitation by a fellow worker, whether in the same agency or not, he or she must report such concerns via established agency reporting mechanisms. 6. Humanitarian workers are obliged to create and maintain an environment which prevents sexual exploitation and abuse and promotes the implementation of their code of conduct. Managers at all levels have particular responsibilities to support and develop systems which maintain this environment. |
| --- | --- |

12. NOTES/DISCLAIMER

- Late submissions will not be accepted.

- NASCP shall verify any or all documents and claims made by applicants and will disqualify consultants with falsified documents and claims.

iii.  If it is determined that submitted documents and claims have been falsified, the consultant may face prosecution in a court of Law.

iv.	NASCP shall not be held responsible for any disqualified proposal as a result of any omission or deletion relating to the submission guidelines.

v.	This advertisement shall not be construed as a contract to any Consultant, nor shall it entitle any Consultant submitting documents to claim any indemnity from NASCP.

vi.	NASCP is not bound to shortlist any Consultant, and reserves the right to annul the bidding process at any time without incurring any liabilities or  providing a reason.

Signed

Management.

B. Format of Curriculum Vitae (CV)

Name :

Complete address :

Profession :

Date of Birth :

Years of professional experience :  	                                    Nationality :

Membership in Professional Societies :

Detailed Tasks Assigned :

Key Qualifications :

[Give an outline of your experience and training most pertinent to tasks on assignment.  Describe degree of responsibility you held on relevant previous assignments and give dates and locations.  One page should be sufficient.]

Education :

[Summarize college/university and other specialized education, giving names of schools, dates attended, and degrees obtained.   A page or less should be sufficient.]

Employment Record :

[Starting with present position, list in reverse order every employment held.  List all positions held since graduation, giving dates, names of employing organizations, titles of positions held, and locations of assignments.  For experience in last ten years, also give types of activities performed and client references, where appropriate.  Use about two pages.]

Languages :

[For each language indicate proficiency: excellent, good, fair, or poor in speaking, reading, and writing.]

Certification :

I, the undersigned, certify that to the best of my knowledge and belief, these data correctly describe me, my qualifications, and my experience.

Date :

[Signature of consultant ]	                                                       Day/Month/Year

Full Name of Candidate :

C. Proposal

[Location, Date]

To :	[Name and address of Procuring Entity]

Mr/Mrs. :

I, the undersigned, offer to provide the consulting services for [Title of consulting services] in accordance with your Letter of Invitation dated [Date].

My fees are [net of taxes, estimated at…, as applicable] monthly.

I hereby submit my Proposal, which includes this Technical and Financial Proposal.

I understand that you are not bound to accept any Proposal you receive.

I remain,

Yours Truly,

Name of the Consultant :

Address :

D.      observations and suggestions

of the consultant on the terms of reference

1.

2.

3.

4.

5.

List of Annexes

Annex A :	Cost Estimate of Services, and Schedule of Rates.

Annex B :	Evaluation Criteria.

Annex A

Cost Estimate of Services

(1) Remuneration

Rate /day 	             Number of Days 	        Total (currency)

in (currency)

(2) Reimbursables

TOTAL COST

ACTIVITY SCHEDULE (Consultant to modify accordingly)

Activity (Work)	                                periods

1st	2nd	3rd	4th	5th	6th	7th	8th	9th	10th	11th	12th

Annex B

EVALUATION CRITERIA

- The selection method to be adopted is Quality Based Selection (QBS)

- The cut-off point is (70%)

- The Criteria, sub-criteria, and point system for the evaluation of the Technical Proposals are:

Points

(i)	Specific experience of the Consultant relevant to the assignment and Educational Qualification:	60

1)	Experience relevant to the assignment              50

- Minimum of 10 years’ experience in HIV/PMTCT programme evaluation or health systems assessments (CV, certificates, or reference letters) (10marks)

- Strong knowledge of Global Fund programmes and Nigeria’s HIV response (5marks)

- Evidence and   Proven experience in mixed-methods research and health programme assessments (Supporting documents, award letters, or contracts for similar jobs) (20)

- Excellent analytical, writing, and stakeholder engagement skills (Evidence such as reports, publications, or letters demonstrating competency) (15marks)

2)    Qualifications relevant to the assignment       10

Advanced degree in Public Health, Medicine, Epidemiology, Health Systems, or related field (10marks)

3) Methodology and Work Plan

(i)Methodology:                                                        (30marks)

(ii) Work Plan:                                                         (10marks)

Total points for criterion (I, II & III):  	100

- Negotiations will be held if required.

See UNSG Bulletin ST/SGB/2003/13 for the definition of sexual exploitation and abuse.

A victim/survivor centered-approach is one for which the victim/survivor’s dignity, experiences, considerations, needs, and resiliencies are placed at the center of the process, from the initial program design to investigating and responding to potential incidents. Consistent with the UN Protocol on Allegations of SEA Involving Implementing Partners, the victim/survivor should be informed, consulted during the decision-making process, and provide consent on the possible use and disclosure of their information. Those interacting with the victim/survivor and/or handling information regarding the allegation will maintain confidentiality, ensure safety of the victim/survivor, and apply victim/survivor-centered principles which are safety, confidentiality, respect, and non-discrimination. When the victim/survivor is a child, the approach will consider the best interests of the child and engage with the family/caregivers as appropriate. Staff and partners should comply with host country and local child welfare and protection legislation and international standards, whichever gives greater protection.